## Arkusz3
Baltic FAB NSA Cooperation Agreement Implementation Plan
No of action | Name of action | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017
|  | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10' | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10' | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10' | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10' | 11 | 12
1 | Supervision and Safety oversight activities
1.1 | NSAs mutual notification about the safety oversight programmes | bar: 2014 01 to 2014 05
1.2 | Development of Common safety oversight programme taking into consideration ICAO, EASA and Eurocontrol supervisory activities | bar: 2014 01 to 2014 12
2 | NSA Coordination Committee
2.1 | Establishment of the Baltic FAB NSA Coordination Committee | bar: 2014 01 to 2014 04
2.2 | Establishment of rules and procedures for notification of any changes to the safety oversight activities. | bar: 2014 01 to 2015 06
2.3 | Adoption of the common format of safety regulatory audit reports and the classification of the findings | bar: 2014 01 to 2015 12
3 | Performance Scheme
3.1 | Setting Baltic FAB Preliminary Targets for RP2 | bar: 2014 01 to 2014 03
3.2 | Common FAB consultation meeting on the draft Perfomance Plan 2015-2019 | bar: 2014 04 to 2014 05
3.3 | Elaboration of the Performance Plan at FAB level | [48 empty] | TBD | bar: 2014 01 to 2014 06
4 | Harmonization of national rules
4.1 | Identification national rules and procedures eligible for harmonization | bar: 2014 01 to 2014 08
4.2 | Creation of the "Common handbook of the Baltic FAB supervisory rules and procedures" | bar: 2014 01 to 2016 06
4.3 | Harmonization of national rules and procedures related to ANS/ATM. | bar: 2014 01 to 2016 06
5 | Information exchange
5.1 | Establishment of the harmonized procedure for exchange and dissemination of safety related information | bar: 2014 01 to 2015 12
5.2 | Establishment of the procedure for exchange of ATM occurence data | bar: 2014 01 to 2014 12
6 | Pool of auditors and experts
6.1 | Creation of a technical experts database executing supervisory activities